## Issues
External Financial and Compliance Audit Report By Hoda Vasi & Co
SL | Issues | Summary
01 | Project Implementation Schedule as indicated in the Grant Agreement was not followed. | The indicative Project Implementation Schedule as was provided in the Grant Agreement was not followed. According to the implementation schedule, activities under the Project such as recruitment procedures should begin from the second quarter of the year 2016, and this will followed by other project activities as set against certain subsequent period of time. However we did not find evidence of any project activities before the year that ended on 30 June 2018. No review of the implementation of Project activities against the implementation schedule was conducted and no revised implementation schedule was prepared for the project.
02 | Work Plan and Implementation Reports were not submitted for the Project. | No work plan was provided on the first period of implementation of the Project to AFD and the European Union. Implementation Reports providing a complete account of all aspects of implementation of the project were not prepared for every twelve (12) month period from the commencement of implementation period of the Grant Agreement.
03 | No Training Program was prepared for ‘Sub-component 3.3- Training of High and Medium Level DWASA Staff’. | No training program was prepared containing the training schedule and defining the procedures relating to selection of selection trainings and participants and conduction of the trainings under ‘Sub-component 3.3-Training of High and Medium Level DWASA Staff’ which is one of the components of the LIC Project.
04 | Inadequate information preserved for the Project Imprest Account in Bangladesh Bank. | During the time of our review we did not find any bank statement for the Project Imprest Account maintained in Bangladesh Bank (BB), the entity only maintained the letters issued by BB during account opening, fund transfers from AFD and fund transfer by BB to the other Project Account.
05 | Provisional forecast of expenditure required for first drawdown was not found. | During the time of our review we have not found any forecast plan of expenditure in case of first drawdown request made by project management unit of LIC.
06 | Required signed contract (amended) with the contractor for Work Lot 7 was not found. | The work contract for Lot 7 was made with Bangladesh Association for Social Advancement (BASA) and the project location was in T&T Colony Bosti, but contractor (BASA) could not commence their work on that particular location due to some complexities observed after the contract was signed with LIC project, which was observed by both the parties and the procuring entity of Project has taken NOC from AFD and AFD required a subsequent signing of an amended contract for the lot-7 for changing the location (new location: Football Ground Camp or FG Camp). But no signed Amended Contract with BASA was found by us, and the initial contract Amount was BDT 34,532,454.
07 | Evaluation process for recruitment of consultants did not comply with the applicable ToR. | In some cases, we observed that consultants’ eligibilities did not match the requirements of the ToR.
08 | Control weaknesses in Procurement Process including non-compliance with AFD Procurement Guideline and Public Procurement Rules (PPR) 2008. | We observed the following issues in relation to procurement process of the LIC Project: a. Notification of awards for contracts with NGOs were not published in media. b. We did not find any signatures of the tenderers or their representatives in the records maintained by the entity for the procurements made under the Project. c. Tender Evaluation Committee (TEC) members did not sign the self-interest declaration sheet for service contract (individually and collectively). d. No medical reports were submitted by any of the consultants of LIC project at the time of appointment. e. Copies of money receipts for tender sales for procurement under the Project were not found during the audit
09 | Sufficient supporting documents relating to training program titled ‘Urban Water and Sanitation’ was not initially preserved by the PMU. | Four participants from DWASA participated in a training program titled ‘Urban Water and Sanitation’ which was held in Singapore and Cambodia during the months of October and November in 2017. Sufficient supporting documents were not found relating to the aforementioned training program which was provided by a training institute namely Agro Paris Tech.
10 | Non-submission of Monthly Statements on work execution, by contractors for certification by the Project. | There were a total of four (4) contractors (NGOs) contracted for total seven (7) Work Lots (Work Lots 1, 2, 3, 4, 6, 7 and 8) under this Project, and bills were already submitted and processed for works executed under work lots 1, 2, 3, 4 and 6. But we observed that none of the contractors submitted Monthly Statements on Work Execution (Monthly Work Details) for certification by the Project management.
11 | A contractor was paid advance payments more than the amount that was allowable as advance as per the contract. | We observed that the Project Management paid more than 30% advance to the contractor for lot 8 (Water & Life Bangladesh). As per contract the contracting amount without Tax and VAT was BDT 29,066,750 and maximum advance payment for that price should be BDT 8,720,025 (30% of contracting amount). But the entity paid to that contractor BDT 9,000,000, which is higher by BDT 279,975 to the maximum advance payable.
12 | Advance payments were not adjusted with each subsequent bill payments. | During the time of our review we have noticed that bills were already paid to the contractors (NGOs) for some lots (1, 2, 3, 4, and 6). But the Advance Payment was not adjusted proportionately with each subsequent bill. We were informed that the full amount of advance will be adjusted when making the final payments to the contractors.
13 | Required reports for pre-construction phase were not submitted by due time and in some cases such reports were not found. | During the time of our review we have noticed that Required reports for pre-construction phase were not submitted before the start of the construction phase as required by the agreement with the contractors (NGOs).
14 | Reporting requirements for the Project’s consultants were not completely followed. | The consultants appointed by the Project are required to prepare two monthly reports and one quarterly plan on the Project. But The consultants only prepared the Monthly Progress Reports on the Project, and did not prepare Management Reports and Quarterly Project Plans for the Project.
15 | Quantitative and Qualitative Reports on Project works were not prepared during the period. | During the audit we did not find any Quantitative Report and/ Qualitative Report to have been generated by the Project’s consultants, and we also did not find any requirements to have been made by the Project management for such reports.
16 | No timesheet and movement register maintained by the PMU for the consultants. | During our audit period, we observed that the Project management do not maintain any timesheet for the consultants’ attendance and leave record which would record the consultants’ works and field movement.
17 | No Inspection Schedule and Inspection Reports are prepared on the field inspections conducted by the Consultants. | During our interview with the Team Leader of the Project’s team of consultants we were informed that the consultants make regular inspection at the construction sites of the contractors under this Project. However we did not find any inspection schedule and no inspection reports were prepared detailing the specifications i.e. time and location of the inspections and the particular observations in relation to the inspections conducted, and no specific references were found to the inspections conducted, in the Monthly Progress Reports submitted the consultants.
18 | Approved reimbursable expenses of consultants were higher than the remuneration proposed by the consultants. | The reimbursable expenses proposed by the consultants during recruitment were attached in Annex-B to the Agreement signed between the consultants and the Project. However we observed that the Project Management approved higher amount of remuneration than the amount proposed by the consultants
19 | Tax Deductible at Source (TDS) and VAT not paid as applicable on payments made by the Project. | The Project did not make any deduction of TDS amounting BDT 294,227 and did not make payments of VAT amounting to BDT 441,341 as applicable on Remuneration and Reimbursable Expenses. The contracts signed with the contractors (NGOs) are exclusive of applicable tax and VAT, therefore the Project is liable to pay applicable TDS and VAT on the payments to the contractors (NGOs). But the Project did not make any payments of TDS and VAT amounting to BDT 7,497,708 and BDT 19,558,036 respectively as applicable on advance and bill payments to the Project’s contractors (NGOs) Furthermore, TDS amounting to total BDT 20,400 was not deducted from honorarium payments for Tender Opening Committee (TOC) and Technical Evaluation Committee (TEC) relating to procurement procedures (payment date 28 November 2017)
Foreign-Aided Projects Audit Directorate
SL | Issues | Summary
01 | Loss of Govt. Revenue due to non-deduction of VAT and IT from contractor's bill. | The authority did not realize the Income Tax from contractors (NGO) bill Tk. 23,23,168.32 and VAT amount of Tk. 29,03,960.40. Authority did not comply with the order No - 06/Mushak/2016 date 2/6/2016.
02 | Received cash from LIC instead of free installation of Water Systems beyond the project objectives, TAPP, Contract agreement and donor. | As per project objectives, TAPP, Contract agreement and donor agreement there were no provision to receipt any cash from LIC. It was free for LIC (Low Income Community) & donor provide the fund as grant money for low income community. As a result the authority of NGO was taken undue benefit from LIC. Some stand post hand pump installation for single family, number of user 3-4 person and inside of the residence which is beyond the project objectives. As a result personal benefit was given to the some person instead of LIC. As per project objectives it was mentioned that to improve the living standard of the low income communities of Dhaka city.
03 | Advanced payment made but not yet adjusted | The authority payment made Tk.1,03,59,736.00 as advance for works. But the advance was not adjusted till to audit on 20.06.2019.
04 | Accrued Bank interest amount was not deposited in to Govt. treasury. | It was seen from bank statement that an amount of Tk.7,86,687.00 was accrued as bank interest during the financial year 2017-18. As per order No.07.111.032.01.OO.015.2011-339, Date:12.05.2011 of Ministry of Finance, accrued bank interest was to be deposited into Govt. Treasury. But the authority did not deposit the same into Govt. treasury.
05 | Irregular payment 3rd advance without adjustment 1st and 2nd advance. | As per Delegation of financial power for development project 2015 Sl-38 (gha) it was mentioned that no second advance can be sanction without 85% adjustment of previous advanced and all advance to be adjusted within 2 month or before 30thJune within the year which is early. The contractor was submitted one (1) nos. Bank Guarantee amount of Tk. 30,00,000 instead of TK 90,00,000 . But the advance was not adjusted till to audit on 20.06.2019.
06 | Loss as Insurance premium VAT due to non execution of insurance against civil works. | But audit revealed that the contractors did not provide insurance coverage in the joint name of employer and the contractor for the period from inception to defect liability period. As per condition of contract the following events are confractor's risks: (a) Loss or damage to the works, Plant and materials. (b) Loss or damage to equipment. (c) Loss or damage to Property. (d) Personal injury or death. As a result Govt. deprived of earning revenue TK. 1,99,207.00 as insurance premium VAT due to non execution of insurance.